{"text_format":"1","workbook":"xlsx","n_sheets":2,"sheets":["Meilensteinplan","Meilensteinplan Bsp"],"not_rendered":{"charts":0,"images":1,"macros":0,"external_links":0,"defined_names":2,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Meilensteinplan","index":0,"n_rows":7,"n_cols":8,"rows_kept":7,"cut":false,"hidden":false,"merged":[]}
["Projekt","PROJEKTNAME",null,null,null,null,"Datum","1900-01-01"]
[]
["Status","Beschreibung Meilenstein","Verantwortung","Termin","kritischer Pfad","Meeting","Planung","Umsetzung"]
[]
[2,"Meeting",null,null,null,1]
[0,"Aktivität Planung",null,null,1,null,1]
[1,"Aktivität Umsetzung",null,null,1,null,null,1]

{"sheet":"Meilensteinplan Bsp","index":1,"n_rows":21,"n_cols":8,"rows_kept":21,"cut":false,"hidden":false,"merged":[]}
["Projekt","Stockhorn",null,null,null,null,"Datum",{"$f":"TODAY()","v":"2021-11-29"}]
[]
["Status","Beschreibung Meilenstein","Verantwortung","Termin","kritischer Pfad","Meeting","Planung","Umsetzung"]
[]
[2,"Betriebs- und Anlagenplanung RSA und BOE","SGR","2021-02-15",1,null,1]
[1,"Freeze Layout BOE und RSA","SGR","2021-03-15",1,null,1]
[null,"Projekt Freeze (Abstimmung BOE und RSA)","SGR","2021-03-20",1,null,1]
[null,"Kosten und Zeitplan BOE und RSA *","SGR","2021-03-31",1,null,1]
[1,"Vorschlag Kommunikationsplan","OMA","2021-04-14",null,null,1]
[1,"Vorschlag Retentionplan (inkl. Abklärungen PK) ","OMA","2021-04-14",null,null,1]
[null,"Kommerzielle Entscheidung für transferierte Produkte","OMA, TGA ","2021-04-14",null,null,1]
[null,"Lösungsvorschlag für Co-Packing Produkte (Hamburger, Sandwich)","OMA","2021-04-14",null,null,1]
[null,"Genehmigung Gesamtprojekt durch Steering Team (Kommunikationsplan, Retentionplan, Kommerzielle Verantwortung, Projektkosten und Umsetzungsplan)","St Team","2021-04-14",1,1,1]
[null,"Genehmigung Gesamtprojekt durch VR 26.4.21","DLU","2021-04-26",1,1,1,1]
[null,"Start Umsetzungsplanung 27.4.21","SGR","2021-04-27",null,null,null,1]
[null,"Kündigung Mietvertrag CS","ALI","2021-05-23",1,null,null,1]
[null,"Kommunikation (tbc)","OMA","2021-09-01",null,null,null,1]
[null,"Abschluss Bau/Umbauarbeiten","SGR","2022-03-31",1,null,null,1]
[null,"Start Umzug Uetendorf","SGR","2022-04-17",1,null,null,1]
[null,"Betriebsbereitschaft RSA/LEP BOE","SGR","2022-05-31",1,null,null,1]
[null,"Rückbau Uetendorf","SGR","2022-05-31",null,null,null,1]