{"text_format":"1","workbook":"xlsx","n_sheets":2,"sheets":["Mijlpalenplan","Mijlpalenplan vb."],"not_rendered":{"charts":0,"images":1,"macros":0,"external_links":0,"defined_names":2,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Mijlpalenplan","index":0,"n_rows":7,"n_cols":8,"rows_kept":7,"cut":false,"hidden":false,"merged":[]}
["Project","Projectnaam",null,null,null,null,"Datum","1900-01-01"]
[]
["Status","Beschrijving mijlpaal","Verantwoording","Termijn","kritiek pad","Vergadering","Planning","Uitvoering"]
[]
[2,"Vergadering",null,null,null,1]
[0,"Activiteitenplanning",null,null,1,null,1]
[1,"Uitvoering van de activiteit",null,null,1,null,null,1]

{"sheet":"Mijlpalenplan vb.","index":1,"n_rows":21,"n_cols":8,"rows_kept":21,"cut":false,"hidden":false,"merged":[]}
["Project","Stockhorn",null,null,null,null,"Datum",{"$f":"TODAY()","v":"2021-11-29"}]
[]
["Status","Beschrijving mijlpaal","Verantwoording","Termijn","kritiek pad","Vergadering","Planning","Uitvoering"]
[]
[2,"Operationele en fabrieksplanning RSA en BOE","SGR","2021-02-15",1,null,1]
[1,"Bevriezing lay-out BOE en RSA","SGR","2021-03-15",1,null,1]
[null,"Projectbevriezing (coördinatie BOE en RSA)","SGR","2021-03-20",1,null,1]
[null,"Kosten en tijdschema BOE en RSA *","SGR","2021-03-31",1,null,1]
[1,"Voorstel communicatieplan","OMA","2021-04-14",null,null,1]
[1,"Voorstel retentieplan (incl. verduidelijkingen PK) ","OMA","2021-04-14",null,null,1]
[null,"Commercieel besluit voor overgedragen producten","OMA, TGA ","2021-04-14",null,null,1]
[null,"Voorgestelde oplossing voor co-packing producten (hamburger, sandwich)","OMA","2021-04-14",null,null,1]
[null,"Goedkeuring van het gehele project door het stuurteam (communicatieplan, retentieplan, commerciële verantwoording, projectkosten en uitvoeringsplan)","St Team","2021-04-14",1,1,1]
[null,"Goedkeuring van het gehele project door VR 26.4.21","DLU","2021-04-26",1,1,1,1]
[null,"Start uitvoeringsplanning 27.4.21","SGR","2021-04-27",null,null,null,1]
[null,"Beëindiging van huurovereenkomst CS","ALI","2021-05-23",1,null,null,1]
[null,"Communicatie (tbc)","OMA","2021-09-01",null,null,null,1]
[null,"Voltooiing van bouw-/verbouwingswerkzaamheden","SGR","2022-03-31",1,null,null,1]
[null,"Start Verhuizing Uetendorf","SGR","2022-04-17",1,null,null,1]
[null,"Operationele paraatheid RSA/LEP BOE","SGR","2022-05-31",1,null,null,1]
[null,"Deconstructie Uetendorf","SGR","2022-05-31",null,null,null,1]